## Bug Report
Bug Report
Release ID | Sprint # | User Story ID | Bug ID | Bug Summary | Severity | Priority | Status | Workaround | Bug Assigned to | Bug Reported by
25.03.3 | Sprint_1 | SCRUM - 11 | SCRUM - 379 | Vendor selection dropdown is not showing on the vendor invoice page to check if POs for a selected vendor are displayed. | Medium | High | Active | Yes (but unclear as a table header filter) | Arya | Anisha T M
|  |  | SCRUM - 380 | Vendor selection dropdown is not showing on the vendor invoice page to verify that POs from other vendors are not displayed when a particular vendor is selected. | Medium | High | Active | Yes (but unclear as a table header filter) | Arya | Anisha T M
|  |  | SCRUM - 384 | Search bar is not sorting based on vendor name only in vendor invoice page | Medium | High | Active | No | Arya | Anisha T M
|  |  | SRCUM-388 | Vendor invoice page table header filter looks like a text field without a clear indication as a filter. | Medium | High | Active | No | Arya | Anisha T M
|  |  | SCRUM - 390 | Dropdowns to select Vendor , work order number and Currency take time to display while adding new PO | Low | Medium | Active | No | Arya | Anisha T M
|  |  | SCRUM - 394 | Work Order number dropdown shows all options before vendor selection while adding new PO. | Medium | High | Active | No | Arya | Anisha T M
|  | SCRUM-18 | SCRUM - 396 | Vendor selection dropdown is not showing on the vendor invoice page to verify that POs lists are changing when swtiching vendor | Medium | High | Active | Yes (but unclear as a table header filter) | Arya | Anisha T M
|  | SCRUM- 32 | SCRUM - 399 | Partial payment: Item quantity modification allows only 1, restricting more than that. | High | High | Active | No | Arya | Anisha T M
|  | SCRUM- 33 | SCRUM - 400 | No field to set advance payment to 20%, preventing verification of percentage-based payment. | High | High | Active | No | Arya | Anisha T M
|  | SCRUM- 34 | SCRUM - 401 | System allowing over-invoicing beyond 100%. | Critical | High | Active | No | Arya | Anisha T M
|  | SCRUM- 41 | SCRUM - 404 | Editing is allowed in draft status only for vendor invoice date (current and previous dates), but some fields remain disabled or read-only and cannot be edited. | Medium | High | Active | No | Arya | Anisha T M
|  |  | SCRUM - 407 | Vendor invoice and payment terms fields are not disabled but also not editable. [UI Error] | Medium | High | Active | No | Arya | Anisha T M
|  | SCRUM-51 | SCRUM - 410 | Debit note added invoice is saving as draft, event after clicking on save as open | High | High | Active | No | Arya | Anisha T M
|  |  | SCRUM - 412 | Debit note not correctly adjusted in vendor invoice, only visible in debit note invoice. | Critical | High | Active | No | Arya | Anisha T M
Severity | Bug Count |  |  |  |  | Bug Status | Bug Count
Critical | 2 |  |  |  |  | New | 0
High | 3 |  |  |  |  | Active | 14
Medium | 8 |  |  |  |  | Ready to Test | 0
Low | 1 |  |  |  |  | Closed | 0
Total Bugs | 14 |  |  |  |  | Re-Open | 0
[6 empty] | Rejected | 0
[6 empty] | Total | 14